## Findings & Understanding
Phase 1.a — Findings & Understanding
Finding | Our Understanding | Why It Matters | Recommended Action
Applications need production stabilization | TOW are already built, but production behavior needs hardening across user flows, access, APIs, and UAT evidence. | Without stabilization, users may continue facing blockers, inconsistent behavior, and avoidable operational friction. | Run structured UAT and convert all validated issues into one agreed stabilization backlog.
Backlog is spread across multiple sources | Bugs, requests, technical debt, build specifications, and UAT findings are not yet consolidated into one execution-ready view. | Duplicate or missed issues can create confusion, delay resolution, and make sign-off difficult. | Create a single consolidated backlog with source, app, owner, priority, impact, recommended action, and acceptance criteria.
Authorization and session behavior need review | Authorization currently spans UI checks, API enforcement, SQL/RLS, PDP/PEP, proxy/session behavior, cookies, and role gates across apps. | Inconsistent access behavior can create security risk, user confusion, or situations where the UI allows an action but the API denies it. | Audit session, cookie behavior, direct API routes, PEP/PDP checks, role gates, RLS, and permission error handling across all apps.
Platform Admin requires UAT attention | Platform Admin is primarily registry/read-focused and has limited automated test coverage today. | Registry or access issues may go unnoticed without a focused manual validation path. | Create a manual UAT checklist and plan smoke tests for critical Platform Admin registry paths.
Azure services are architecture inputs, not automatic scope | Microsoft Entra ID is relevant for identity; Azure RBAC, ARM, API Management, and Function Apps may support future governance or integrations if formally approved. | Assuming unapproved Azure implementation could expand scope beyond production stabilization. | Separate current evidence from future recommendations and treat Azure service expansion as an architecture decision.
UAT should validate real user journeys | Stabilization should be confirmed through role-based user journeys, not only through developer tests. | Automated tests may not catch all real workflow issues seen by business users. | Validate login/session, role access, navigation, submission, data rendering, and error handling through structured UAT.
KB should be browse-first | Users should browse content through hierarchy, article pages, search, breadcrumbs, and internal links. | Improves adoption and avoids making chat the only way to access knowledge. | Keep hierarchy and Markdown article experience as the primary user flow.
Foundations already exist | Existing platform already has KB schema, hierarchy, Markdown content, approval workflow, Supabase, pgvector, OOO APIs, and MCP surface. | This means Phase 1.b is completion and hardening, not a rebuild. | Reuse existing architecture and avoid unnecessary redesign.
Retrieval readiness blocker | Approved content may not appear in query/search because the document status used during embedding does not match retrieval filtering. | If approved articles are not searchable, users may lose trust in KB retrieval. | Complete PR-1 validation and merge status mismatch fix first.
Authorization needs hardening | Viewer, editor, admin behavior must be consistent across KB Admin and OOO APIs. | Prevents draft or restricted content from becoming visible to the wrong users. | Perform route/API authorization audit before expanding new UI routes.
OOO viewer is incomplete | OOO has KB APIs, but the user-facing KB viewer route is not fully implemented. | TOW users cannot browse the KB properly inside the main application yet. | Build OOO KB viewer after retrieval and auth are stable.
Admin UX gaps remain | Admin paths still need polish: create modal, counts, row links, actions, and removal of critical stubs. | Makes admin workflow smoother for creating, approving, and maintaining articles. | Handle admin completion after core retrieval, auth, browse, and OOO viewer work.

## Unused Code Analysis
Detailed Findings — Safe Removable Candidates
App / Package | File Path | Component / Function / Test Case Name | Why It Appears Unused | Can It Be Removed? | Impact If Removed
apps/ooo | components/items/list/items-multi-view.tsx | ItemsMultiView | Zero production imports; only stale test mock | Yes | Removes dead list UI; requires test mock update
apps/ooo | components/items/list/item-row-actions.tsx | ItemRowActions | Only imported by items-multi-view.tsx | Yes | None if parent removed
apps/ooo | components/items/list/bulk-action-toolbar.tsx | BulkActionToolbar | Only imported by items-multi-view.tsx | Yes | None if parent removed
apps/ooo | components/goal-detail/use-manage-hierarchy-wizard.ts | useManageHierarchyWizard | Zero imports in repository | Yes | None expected
apps/ooo | components/items/list/index.ts | barrel export | Empty barrel export only | Yes | None expected
apps/ooo | components/global/forms/index.ts | barrel export | Empty barrel export only | Yes | None expected
apps/ooo | components/__tests__/list-detail-client.test.tsx | ItemsMultiView mock | Mocks component no longer used | Yes | Test stays misleading if not updated
packages/utils | src/type-normalization.ts | normalizeOwner and related helpers | Zero app imports found | Yes | None if no external consumers
packages/types | src/index.ts | OOOCategory, KBWorkflow | Deprecated aliases; zero consumers found | Yes | None expected if confirmed
apps/kb-admin | src/lib/knowledge-base/workflow-states.ts | updateWorkflowStatus (+ 3 siblings) | Zero production imports; superseded by content.ts | Yes | None — approval uses updateArticleContentStatus
apps/kb-admin | src/lib/rate-limit.ts | rateLimit | Zero importers; /api/query unprotected | Yes | No rate limit on query API
apps/kb-admin | src/lib/auth/auth-helpers.ts | requireKBAdmin | Never imported | Yes | None
apps/kb-admin | src/lib/knowledge-base/hierarchy-nodes.ts | getHierarchyNodesByType | Zero callers | Yes | None if hierarchy listing unused
apps/kb-admin | src/lib/knowledge-base/hierarchy-path.ts | getDocumentsByHierarchyPath | Zero callers | Yes | None today
apps/kb-admin | src/lib/knowledge-base/versions.ts | createContentVersion, getContentVersion | Approval inlines upsert in content.ts | Yes | getContentVersions still used
apps/kb-admin | src/lib/audit.ts | logArticleContentChange, logWorkflowChange | Zero callers | Yes | logDocumentChange still used
apps/kb-admin | src/lib/knowledge-hierarchy.ts | re-export shim | Single API consumer | Yes | After import path fix
apps/kb-admin | src/lib/supabase/middleware.ts | re-export | Zero consumers | Yes | None
apps/kb-admin | src/components/admin/index.ts | barrel | No @/components/admin imports | Yes | None
apps/kb-admin | src/components/admin/llm-observability/index.ts | barrel | Page imports client directly | Yes | None
apps/kb-admin | dummy | artifact | Empty Jupyter JSON | Yes | None
packages/types | src/index.ts | KBWorkflow alias | Deprecated; zero imports | Yes | None if external unused
apps/kb-admin | src/__tests__/lib/knowledge-base/workflow-states.test.ts | full suite | Tests dead module | Yes | With module removal