## Oakbridge Issues Tracker
S.No | Title | Description | Priority | Status (Current) | Replicated in App | Findings
1 | REQUEST: Adding Services to SWOT teams | Need all people from the CSAMS email group added to Commercial Line and PL Service email group added to Personal Line. | P1 | Open | Yes | Commercial Lines team contains only 3 members. The required CLAIMS email group members are not fully mapped to this team.
2 | FEATURE: Voting | Allow each team member to vote for any item, not just one. | P1 | Open | Yes | Created a new item ("Voting test") and verified the complete item details page. No voting option/button is available anywhere in the UI. Feature is missing
3 | Not all Users are seeing Public Lists in Shared | Public/shared lists are not visible for all users. | P1 | Open | Yes | Only one shared/public list (site Bugs & request) is visable under shared. Expected additional public list are not visable. Issue replicted
4 | Goals: Team Dropdown is showing all teams | All teams dropdown is showing all teams and not filtered for user eligible teams. | P1 | Open | No | Verified the Goal creation screen. The Primary Team dropdown displays only the user's accessible team ("TOW App"). Other teams are not visible. Could not reproduce the reported issue.
5 | FEATURE: Transfer Goal Ownership to Another Team | Need functionality to transfer goal ownership to another team. | P1 | Open | No | Verified the goal details page. Since the current user is not the goal owner/accountable user, the transfer ownership functionality cannot be validated.
6 | FEATURE: Ability to Delete Goals | Need ability to delete goals by accountable party. | P2 | Open | Yes | Opened the goal detail page and verified the Actions menu. Only the Clone option is available because the goal is in Read Only mode. Delete option is not available for the current user
7 | Bug: Reading Items to Team – Search Dialogue | There is no visual showing the selection of the record. | P2 | Open | Yes | Search dialog returns matching items. However, the current user cannot select or add a relationship because the item is in Read Only mode.
8 | Search Feature returns null when there are known results | Search returns null even when records exist. | P2 | Open | Not | Search returned the expected result ("TOW App (TheOakbridgeWay.com)"). Could not reproduce the reported issue.
9 | FEATURE: Cascading Message | Ability to push organization-wide cascading message. | P2 | Open | Yes | Verified the goal Actions menu. Only the "Clone" option is available; no Cascading Message or organization message feature is present. Issue replicated.
10 | FEATURE: Publicly Available Forum | Publicly available forum/team feature request. | P2 | In IDS | Yes | Opened the goal detail page and verified the Actions menu. Only the Clone option is available because the goal is in Read Only mode. No edit or delete actions are available for the current user.
11 | FEATURE: Pre-defined Boxes | Pre-defined boxes for each required step. | P3 | Open | Yes | Verified Create New Item. Only one Description field is available. Separate predefined boxes (Root Problem, Symptoms, Considerations, DoD & Dependencies) are missing. Issue replicated.
12 | TOW Vision to KB Article – Full Integration | Future evolution path for TOW vision to KB article integration. | P3 | Open | No | Verified the Vision page. Mission, Vision, and Purpose sections load correctly and are displayed without any UI or functional issues. Could not reproduce the reported issue.
13 | BUG: List Selection | No-list/unassigned owner option should be restricted. | P3 | Open | Yes | Verified the Create New Item screen. The form contains only a single Description field. Separate predefined boxes for Root Problem, Symptoms, Considerations, and Definition of Done & Dependencies are not available. Issue replicated.
14 | BUG: Submit Goal Draft | Submit goal draft behavior issue. | P3 | In IDS | Yes | Verified the Goal creation wizard. The Next button remains disabled after entering the required details, preventing completion of the draft submission flow. Unable to verify the Submit Goal Draft functionality due to the blocked workflow.
15 | FEATURE: Export Functions | Export functions such as IFC Auto Export and VTO Auto Export. | P3 | Open | Yes | Opened the FEATURE: Export Functions item details page and verified the available actions. No export functionality is available from the item details page. The Add button remains disabled, and no Export option is present. The requested Export Functions feature could not be validated from this screen.
16 | MASTER: My Profile Rebuild | My Profile rebuild requirements. | P3 | Open | Yes | Verified the user profile page. The page displays user statistics and account information, but no Export Functions or export-related controls are available. The requested Export Functions feature could not be validated from the profile page.
17 | MASTER: Code Repo Cleanup | Code repo cleanup. | P3 | Open
18 | MASTER: Comments and Field History | Comments and field history enhancements. | P3 | Open | No | Verified the Comments functionality. Comments can be added successfully and are displayed correctly. However, the History section does not display the expected field change records, indicating the issue is still reproducible.
19 | Goal Drill Rollup | Goal rollup should connect correctly to leadership initiative. | P4 | Solved | No | Verified the Cascading Goals tab on the goal detail page. The page loaded successfully and displayed the "No direct relationships" message without any errors or UI issues. Could not reproduce the reported issue.
20 | MASTER: Advanced Enhancements | Advanced enhancements under AI knowledge analysis. | P1 | In IDS | No | Verified the History section on the item detail page. Field history records are displayed correctly with the changed field, user, timestamp, old value, and new value. The history functionality is working as expected, and the reported issue could not be reproduced.
21 | FEATURE: Executive Security Role | Executive security role requirement. | P4 | Open | Yes | Verified the FEATURE: Executive Security Role item. The Type and Category dropdowns are accessible, but Team/List modifications are restricted due to insufficient permissions. The Add button remains disabled, preventing changes from being saved. The application is enforcing permissions correctly, and the reported issue could not be reproduced.
22 | Text Formatting | Text formatting support. | P3 | Open | Yes | Verified Description editor. Basic formatting options are available, but Underline and advanced/nested list formatting are missing. Issue replicated.
23 | Item Relationships | Item relationship and Rock reference behavior. | P3 | Open | No | Verified the Item Relationships feature. Successfully searched for an existing item, added it as a related item, and confirmed it appears under the Relationships tab with the correct relationship type, owner, team, and date linked. Could not reproduce the reported issue.
24 | Add RACI when creating Issue | Add RACI options while creating an issue. | P3 | Open | No | Verified the RACI item creation functionality. Entered the required details and successfully created a new item. The item appeared correctly in the Site Bugs & Requests list with the expected title, description, type, category, owner, and RACI assignment. Could not reproduce the reported issue.
25 | Goal Delete Button Not Visible | Goal delete button is not visible. | P3 | Open | Not Tested | Unable to fully validate. Current user is not the goal owner/accountable user, so Delete button visibility cannot be confirmed for an authorized user.
26 | FEATURE: Color Coding | Color pickers and color coding support. | P3 | Open | Yes | Verified color coding for badges. Some Status/Priority/Type/Category values are missing colors or displaying incorrect colors. Issue replicated.
27 | FEATURE: Login Auth – Oakbridge Grade – Viewer Automatic | Login auth and viewer automatic behavior. | P3 | Open
28 | Site Bugs – Not Available in Side Bar | For cole when screen is sharing | P3 | Open | No | Verified the left sidebar. Site Bugs & Requests is available under the Shared section and can be opened successfully. Could not reproduce the reported issue.
29 | BUG: The Banner displays 'Pending Movement' when archived and locked | Banner displays wrong status when archived and locked. | P3 | Open | Yes | Verified an archived and locked item. The banner displays "Pending movement approval" while the item is in Archived and Locked state. Issue replicated.
30 | Visual Diagrams – Excel Figure / Founder Image | Visual diagrams / Excel figure / founder image request. | P3 | Open | Yes | Opened the "Visual Diagrams – Excalidraw (YouTube video)" item. No Excalidraw diagram, embedded YouTube video, or related visual content was found. Issue replicated.
31 | FEATURE: Filtering Values (UI and Repo) | Filtering values should be available in UI and repo. | P3 | Open | No | Search/filter correctly returns matching items. The filtered list displays expected records and the UI remains aligned. No filtering or UI issue observed.
32 | FEATURE: Add Attachments to List Items | Add attachments to list items. | P3 | Open | Yes | Verified the item detail page for attachments. No attachment section, upload button, paperclip icon, or file picker is available. Users cannot upload or manage attachments for list items. Issue replicated.
33 | FEATURE: Connected Goals | On the list view- see if the goal connects to the larger objective or not "Has Parent", "Has Child" | P3 | Open | No | Successfully linked a goal to the item using the Link Goal functionality. The linked goal is displayed correctly under the Related Goal section, and no issues were observed.
34 | MASTER: Admin Section and Pages Rebuild | Dialogues Color pickers-are they even used? | P3 | Open | Not Tested | Unable to test the Admin Section because the current user account does not have Admin access. The Admin menu is not available in either the left navigation or the profile menu, preventing verification of the Admin pages and functionality.
35 | BUG: Tab Data (Teams) Showing Up | Also added the scope to the teams rebuild | P3 | Open | Yes | Verified Teams/global search by searching for “test”. Multiple test/debug records are visible to the user, including “Testing Item for Debug”, “TESTING ITEM - DELETE”, and “Visibility: Permission Rebuild Testing - Non-Member”. Test data is exposed in the application. Issue replicated.
36 | FEATURE: See Titles of Other Teams | Ability to see titles of other teams. | P3 | Open | No | Verified Global Search. Item titles are displayed in the search results without exposing underlying details. Feature is working as expected.
37 | FEATURE: Recent Items | Recent items feature. | P3 | In IDS | No | Recent Item feature is available at the bottom of every page. Feature is working as expected
38 | CLEANUP: Unused Fields from Various Tables | Remove unused fields from various tables. | P3 | Open | No | Verified the Dashboard after opening multiple items. Recently Viewed is updated correctly with recently accessed items, and no unexpected or unused fields are displayed. Could not reproduce the reported issue.
39 | SEC: Remove Default PW | Still loggings on create - Creating an issue in the future | P3 | Open
40 | FEATURE: AI Dialogue to Generate the Root Problem | AI dialogue to generate root problem. | P3 | Open | Yes | Searched the application using the global search for "Dialogue". The search returned only feature request items, including "AI Dialogue to generate the Root problem". No AI dialogue, AI assistant, or root problem generation functionality is available in the current application. The requested feature could not be validated because it is not implemented.
41 | FEATURE: Item Due Date – Default Date | Default due date behavior. | P3 | Open | Yes | Created a new item and verified that the Due Date is automatically populated with a default value approximately 30 days from the creation date. Current behavior matches the description provided in the feature request.
42 | FEATURE: Adopted Ideas | Display adopted ideas of the company. | P3 | In IDS | Yes | Searched the application using the global search for "Adopted". The search returned only the feature request item (FEATURE: Adopted Ideas). No dedicated "Adopted Ideas" page or functionality is available in the application. The requested feature could not be validated and appears to be unimplemented.
43 | FEATURE: Managing Filtering Tags | Inline hastag tags inline in text areas. 1. This is completely unused right now. 2. This should assist with the LLM RAG setting. | P3 | Open | Yes | Verified the "Managing & Filtering Tags" feature. While creating and viewing an item, no functional Tags field or tag filtering capability is available. Inline hashtags entered in the description are treated as plain text and cannot be managed or used for filtering. Issue replicated.
44 | FEATURE: User Reports and Audit Trail | User reports and audit trail. | P3 | Open

## Summary
Priority | Count
P1 | 6
P2 | 5
P3 | 31
P4 | 2
Total | 44